AGENTIC AI WHATSAPP BOT

Fenestration Industry — RFQ Automation Platform

Product Requirements Document ¦ Statement of Work ¦ User Flow & Wireframes

Version 1.0  —  MVP Edition

Prepared for: Senior Python Developer / AIML

Classification: Confidential — Internal Use Only

# Table of Contents

Table of Contents	2

1. Executive Summary & Objectives	5

1.1 Executive Summary	5

1.2 Business Objectives	5

1.3 Key Performance Indicators (KPIs)	5

2. Target Audience & User Personas	6

Persona 1: Procurement Manager / Manufacturer (Primary)	6

Persona 2: Material Supplier (Secondary)	6

Persona 3: System Administrator (Technical)	6

3. Detailed User Stories & Acceptance Criteria	7

Workflow 1: Requirement Understanding & RFQ Generation	7

US-001: Natural Language Requirement Parsing	7

US-002: RFQ Broadcast to Supplier List	7

Workflow 2: Multimodal Ingestion & Parsing	7

US-003: Plain Text Quote Parsing	7

US-004: PDF Quote Parsing	8

US-005: Image/Photo Quote Parsing (Handwritten & Printed)	8

US-006: Audio/Voice Note Quote Parsing	8

Workflow 3: Comparative Analysis & Notification	8

US-007: Quote Compilation & Comparison	8

Workflow 4: Voice-Activated Database Execution	9

US-008: Voice Command Transcription & Intent Extraction	9

US-009: Ambiguous Command Handling	9

4. Non-Functional Requirements	10

4.1 Performance & Latency	10

4.2 Scalability	10

4.3 Security & Authentication	10

4.4 Reliability & Availability	10

5. Edge Cases & Error Handling	12

5.1 AI Hallucination Prevention	12

5.2 Unreadable / Corrupt Media	12

5.3 Ambiguous Voice Commands	12

5.4 Supplier Edge Cases	13

5.5 Network & API Failures	13

6. Database Architecture Requirements	14

6.1 Core Entity Tables	14

Table: products	14

Table: suppliers	14

Table: rfq_sessions	14

Table: rfq_line_items	15

Table: supplier_quotes	15

Table: quote_line_items	15

Table: inventory	16

Table: pricing	16

Table: audit_log	16

1. Project Scope	18

1.1 In-Scope for MVP	18

Core Platform	18

Workflow 1: RFQ Generation	18

Workflow 2: Multimodal Ingestion	18

Workflow 3: Comparative Analysis	18

Workflow 4: Voice-to-DB	18

1.2 Out-of-Scope (Future Phases)	19

2. Technical Stack Recommendations	20

2.1 Core Backend	20

2.2 AI / LLM Layer	20

2.3 WhatsApp Integration	20

2.4 Infrastructure	21

2.5 Development Tools & Testing	21

3. Phased Implementation Plan	22

Phase 1: Core Infrastructure & WhatsApp Authentication	22

Phase 1 Acceptance Criteria	22

Phase 2: RFQ Generation & Multimodal Parsing Pipeline	22

Phase 3: Comparison Engine & Agentic Voice-to-DB	23

3.1 Timeline Summary	23

3.2 Assumptions & Dependencies	23

1. Manufacturer WhatsApp UX Flow	25

Flow 1A: Sending a Requirement & RFQ Generation	25

Flow 1B: Receiving Quote Notifications	26

Flow 1C: Requesting Comparison Report	27

Flow 1D: Voice-Activated Database Update	28

2. Supplier WhatsApp UX Flow	30

Flow 2A: Receiving & Responding to an RFQ	30

Flow 2B: Error / Retry Scenario	31

3. Backend Architecture Flow	33

3.1 Inbound Message Processing Flow (Webhook → LLM Router)	33

3.2 RFQ Generation Flow (Manufacturer → Broadcast)	34

3.3 Multimodal Quote Ingestion Flow	35

3.4 Voice-to-DB Execution Flow	36

3.5 Service Architecture Diagram (Text Representation)	38

DOCUMENT 1

PRODUCT REQUIREMENTS DOCUMENT (PRD)

Agentic AI WhatsApp RFQ Bot — Fenestration Industry

# 1. Executive Summary & Objectives

## 1.1 Executive Summary

The Fenestration Industry RFQ Automation Platform is an AI-powered WhatsApp bot designed to eliminate the manual, error-prone process of requesting and collating supplier quotations. Manufacturers in the window and door manufacturing sector currently spend significant time emailing, calling, and manually comparing quotes from multiple suppliers — a process that is slow, inconsistent, and prone to data entry errors.

This platform automates the entire RFQ lifecycle: from requirement parsing and broadcast, through multimodal quote ingestion (text, PDF, image, audio), to comparative analysis and voice-activated database execution. The system is built on a FastAPI backend, WhatsApp Business Cloud API, and a multi-agent AI layer orchestrating LLMs, Vision models, and Speech-to-Text engines.

## 1.2 Business Objectives

- Reduce average RFQ cycle time from 3–5 days to under 4 hours

- Eliminate manual data entry errors in supplier pricing updates (target: >95% accuracy)

- Standardize supplier response ingestion regardless of format (text, PDF, image, audio)

- Enable one-touch, voice-activated database updates for procurement managers

- Provide a fully auditable RFQ trail with timestamps and supplier attribution

- Build a reusable multimodal AI pipeline extensible to other manufacturing verticals

## 1.3 Key Performance Indicators (KPIs)

| KPI | Baseline (Manual) | MVP Target |
| --- | --- | --- |
| RFQ Cycle Time | 3–5 Business Days | < 4 Hours |
| Data Extraction Accuracy | ~70% (human error) | > 95% (AI + human review) |
| Supplier Response Coverage | Variable | 100% of connected suppliers |
| Voice Command Success Rate | N/A | > 90% intent recognition |
| DB Update Latency | Manual (hours) | < 30 seconds post-approval |
| Formats Supported | Email text only | Text, PDF, Image, Audio |

# 2. Target Audience & User Personas

## Persona 1: Procurement Manager / Manufacturer (Primary)

Name: Rajesh Mehta ¦ Role: Procurement Manager, Mid-size Fenestration Manufacturer

Tech Literacy: Moderate — comfortable with WhatsApp, basic smartphone usage

Pain Points: Manually calls/messages 8–12 suppliers per RFQ; spends 2–3 hrs consolidating quotes into Excel; misses better prices due to late replies; forgets to update ERP pricing tables.

Goals: Get a consolidated price comparison on WhatsApp without switching tools; update pricing database with a voice note.

WhatsApp Usage: Daily, primary communication channel for business.

## Persona 2: Material Supplier (Secondary)

Name: Anita Shah ¦ Role: Sales Executive, Glass & Aluminium Supplier

Tech Literacy: Low-to-Moderate — uses WhatsApp Business daily, not technical

Pain Points: Receives vague, inconsistent RFQs; manually types rates in different formats per customer preference.

Goals: Respond to RFQs quickly without extra friction; get confirmation of submission.

Interaction Mode: Passive receiver of RFQ broadcasts; replies in their own natural format (text, photo of ledger, PDF, voice).

## Persona 3: System Administrator (Technical)

Name: Dev Team / IT Admin

Responsibilities: Manage supplier contact lists; configure product catalogs; monitor AI parsing logs; handle escalations for unrecognized formats.

Access: Admin dashboard (future phase); direct DB access for corrections.

# 3. Detailed User Stories & Acceptance Criteria

## Workflow 1: Requirement Understanding & RFQ Generation

### US-001: Natural Language Requirement Parsing

As a Procurement Manager, I want to send a raw requirement in plain language to the WhatsApp bot so that the bot generates a professional, standardized RFQ without me having to format it manually.

ACCEPTANCE CRITERIA

- GIVEN the manufacturer sends a message like 'Need rates for 50 units of 4mm toughened glass', WHEN the bot processes it, THEN it extracts: material_type='toughened glass', thickness='4mm', quantity=50, unit='units'

- The bot must handle incomplete inputs (missing unit, missing quantity) and prompt for clarification via a WhatsApp reply before broadcasting

- Generated RFQ message must include: product specification, quantity, unit of measure, required delivery date (prompted if missing), and a unique RFQ reference ID (e.g., RFQ-2025-0041)

- The manufacturer receives a preview of the RFQ with a WhatsApp quick-reply confirmation button before broadcast

- Parsing must complete within 3 seconds of message receipt

### US-002: RFQ Broadcast to Supplier List

As a Procurement Manager, I want the bot to automatically send the approved RFQ to all relevant suppliers in my predefined list so that I do not have to message each supplier individually.

ACCEPTANCE CRITERIA

- GIVEN the manufacturer confirms the RFQ preview, WHEN broadcast is triggered, THEN all active suppliers in the product-category-matched supplier list receive the RFQ within 60 seconds

- Each supplier message includes the RFQ reference ID, product specs, quantity, deadline for response, and the manufacturer's contact for queries

- Failed deliveries (WhatsApp API errors) are retried up to 3 times with exponential backoff; failures are logged and the manufacturer is notified

- Broadcast supports up to 50 suppliers simultaneously per RFQ

## Workflow 2: Multimodal Ingestion & Parsing

### US-003: Plain Text Quote Parsing

As a system, I must correctly parse supplier quotes received as plain text WhatsApp messages and extract all pricing and term data into a structured JSON object.

ACCEPTANCE CRITERIA

- System identifies the message as a quote by matching the RFQ reference ID in the text

- Extracted JSON must include: supplier_id, rfq_id, line_items[{product, quantity, unit_price, currency, gst_rate, delivery_days, validity_days}], total_price, notes

- Handles informal language: 'rate is 250 per sq ft + 18% gst, delivery in 7 days' correctly maps to unit_price=250, gst_rate=18, delivery_days=7

- Parsing confidence score >= 0.85 required; below threshold triggers human-review flag

### US-004: PDF Quote Parsing

As a system, I must extract structured pricing data from supplier PDFs including scanned documents, formatted quotation templates, and complex multi-product tables.

ACCEPTANCE CRITERIA

- System downloads the PDF from WhatsApp media URL, converts to images, and passes through Vision LLM pipeline

- Handles multi-page PDFs; extracts data from tables, header sections (supplier name, date, validity)

- If PDF is encrypted or corrupted, system flags for manual review and notifies the manufacturer

- Processing time: <= 15 seconds for PDFs up to 10 pages

- Duplicate submission detection: if same supplier submits for same RFQ_ID again, the system asks for confirmation before overwriting

### US-005: Image/Photo Quote Parsing (Handwritten & Printed)

As a system, I must extract pricing data from photos of handwritten ledgers, printed price lists, and photographed invoices using Vision LLM OCR capabilities.

ACCEPTANCE CRITERIA

- Accepts JPEG, PNG, WEBP image formats up to 10MB

- Achieves >85% field extraction accuracy on clearly legible handwritten text

- For low-confidence extractions (< 0.75), returns a structured partial result with flagged fields marked as 'requires_review': true

- System must NOT hallucinate numeric values; any extracted price must be traceable back to a pixel region in the source image (bounding box logged)

### US-006: Audio/Voice Note Quote Parsing

As a supplier, I want to reply to the RFQ with a voice note stating my prices so that I do not have to type a formal quotation.

ACCEPTANCE CRITERIA

- System downloads audio file, transcribes using Whisper (or equivalent), then passes transcript through LLM for structured extraction

- Supported languages: English, Hindi (Hinglish mix must be handled)

- Transcription + extraction completes within 20 seconds for audio up to 60 seconds

- Extracted data follows the same JSON schema as other modalities

- If audio is inaudible or extraction confidence < 0.70, supplier is asked to re-submit in another format

## Workflow 3: Comparative Analysis & Notification

### US-007: Quote Compilation & Comparison

As a Procurement Manager, I want to receive a structured, easy-to-read comparative summary of all supplier quotes on WhatsApp so that I can make a quick, informed decision.

ACCEPTANCE CRITERIA

- Comparison triggered manually (manufacturer sends 'compare RFQ-2025-0041') OR automatically after all suppliers have responded OR after the response deadline expires

- Comparison message is formatted as a WhatsApp-friendly table (using monospaced text formatting) showing: Supplier | Unit Price | GST | Delivery | Total Cost | Notes

- Highlights the lowest total cost option with a checkmark indicator

- Includes a 'MISSING' flag for suppliers who have not yet responded

- Summary message length must not exceed WhatsApp character limits; splits into multiple messages if required

## Workflow 4: Voice-Activated Database Execution

### US-008: Voice Command Transcription & Intent Extraction

As a Procurement Manager, I want to send a voice note like 'p1 material price 50, 30 units' and have the bot correctly map this to a database update without me typing anything.

ACCEPTANCE CRITERIA

- Bot receives audio, transcribes, and uses function-calling/tool-use to identify intent as 'update_pricing' or 'update_inventory'

- Correctly resolves entity mapping: 'p1' -> product_id from context/session, 'material price' -> pricing.material_cost, '30 units' -> inventory.quantity

- Before executing, bot sends a WhatsApp confirmation message: 'Confirm: Update product [Glass 4mm Toughened] — material_cost = INR 50, quantity = 30 units? Reply YES / NO'

- Database update executes only upon explicit 'YES' reply

- Success confirmation message sent back to manufacturer within 5 seconds of 'YES'

- Full audit log entry created: who, what, when, source (voice_note_id)

### US-009: Ambiguous Command Handling

As a system, I must handle ambiguous or incomplete voice commands gracefully without executing incorrect database updates.

ACCEPTANCE CRITERIA

- If intent confidence < 0.80, bot asks a clarifying question instead of proceeding

- If entity cannot be resolved (e.g., 'p1' matches multiple products in DB), bot presents a numbered list and asks the user to select

- Maximum 2 rounds of clarification; if unresolved, escalates to manual review queue

- No database write is ever executed without an explicit human confirmation step

# 4. Non-Functional Requirements

## 4.1 Performance & Latency

| Operation | Max Acceptable Latency | Notes |
| --- | --- | --- |
| Text message parsing | < 3 seconds | End-to-end from webhook to reply |
| RFQ broadcast (50 suppliers) | < 60 seconds | Async queue-based |
| PDF parsing (up to 10 pages) | < 15 seconds | Vision LLM pipeline |
| Image/photo OCR | < 10 seconds | Single image |
| Audio transcription + extraction | < 20 seconds | 60s audio clip |
| Voice-to-DB intent extraction | < 5 seconds | Post-transcription |
| DB confirmation + write | < 5 seconds | Post-YES confirmation |
| Comparison report generation | < 8 seconds | For up to 20 suppliers |

## 4.2 Scalability

- System must handle 100 concurrent RFQ sessions without performance degradation

- Stateless FastAPI design; horizontal scaling via Docker/Kubernetes

- AI inference calls must be asynchronous and non-blocking (Celery task queue or asyncio)

- Database connection pooling (min: 5, max: 50 connections)

- WhatsApp API rate limits: enforce per-number rate limiting (1000 msgs/day Business API limit)

## 4.3 Security & Authentication

- WhatsApp Webhook: Validate X-Hub-Signature-256 HMAC on every inbound request

- All API keys (Meta, OpenAI/Anthropic, DB) stored in environment variables / secrets manager (AWS Secrets Manager or HashiCorp Vault)

- Inter-service communication over HTTPS/TLS 1.3 only

- Database: Parameterized queries only; no raw SQL string interpolation (prevent SQL injection)

- Manufacturer authentication: Phone number verified via WhatsApp Business; optional PIN for DB write operations

- PII handling: Supplier contact details encrypted at rest (AES-256); GDPR-compliant data retention policies

- Session tokens: Manufacturer conversation state stored in Redis with 24hr TTL

- All AI model API calls logged with request/response hashes for audit purposes (no PII in logs)

## 4.4 Reliability & Availability

- Target uptime: 99.5% (allows ~4 hours/month downtime)

- Webhook endpoint: Health check endpoint at /health returning 200 OK

- Graceful degradation: If Vision LLM is unavailable, system flags quote for manual entry and notifies user

- All DB writes wrapped in transactions with rollback on failure

- Dead letter queue for failed WhatsApp outbound messages

# 5. Edge Cases & Error Handling

## 5.1 AI Hallucination Prevention

CRITICAL RISK: LLMs may generate plausible but incorrect numeric values (prices, quantities).

Mitigation Strategies:

1. Grounding Validation: All extracted prices must fall within a configurable min/max range per product category (e.g., 4mm glass: INR 80–500/sqft). Out-of-range values trigger a review flag.

2. Cross-field Consistency Check: total_price must approximately equal unit_price * quantity * (1 + gst_rate/100). Discrepancy > 5% flags for review.

3. Source Traceability: Vision pipeline must log bounding box coordinates for each extracted numeric value. Auditor can view the original source region.

4. Confidence Thresholds: No silent failures — all low-confidence extractions are surfaced to the manufacturer before comparison is generated.

5. Human-in-the-Loop Gate: Mandatory confirmation before any DB write, regardless of confidence.

## 5.2 Unreadable / Corrupt Media

| Scenario | Handling |
| --- | --- |
| PDF encrypted or password-protected | Reply to supplier: 'PDF could not be opened. Please send without password protection.' Flag RFQ item as pending. |
| Image too blurry / low resolution | Attempt extraction; if confidence < 0.60, reply to supplier requesting a clearer photo. |
| Audio file corrupted / too short (< 2s) | Reply to supplier: 'Audio could not be processed. Please re-send or type your quote.' Do not attempt extraction. |
| PDF > 50MB or image > 10MB | Reject at webhook ingestion layer with friendly error message to supplier. |
| Unsupported file format (e.g., .xls) | Notify supplier of accepted formats; do not attempt parsing. |
| WhatsApp media URL expired (> 5 min) | Retry download 3x with 30s intervals; if failed, mark quote as 'media_expired' and notify manufacturer. |

## 5.3 Ambiguous Voice Commands

- 'p1 price 50' — product 'p1' maps to multiple items: present numbered list, ask user to confirm product

- Numbers transcribed incorrectly (fifty vs 15): LLM must detect and flag numeric ambiguity

- Mixed language commands (Hinglish): 'glass ka price update karo 250 per sqft' — must handle code-switching

- Command with no matching product in DB: 'update XYZ price' — reply with 'Product XYZ not found. Did you mean: [list of close matches]?'

## 5.4 Supplier Edge Cases

- Supplier sends quote for wrong RFQ ID: Cross-reference; if no match found, ask supplier to confirm RFQ reference

- Supplier sends multiple quotes for same RFQ (revision): Store as a new version; show latest in comparison with 'REVISED' tag

- Supplier sends partial quote (only some line items): Mark missing items as null; include supplier in comparison with partial flag

- Unknown supplier (not in system) sends a quote: Quarantine message; notify admin to verify and onboard supplier

## 5.5 Network & API Failures

- WhatsApp API rate limit hit: Implement token bucket rate limiter; queue excess messages with priority ordering

- LLM API timeout (> 30s): Retry once; if second attempt fails, mark for manual processing and notify manufacturer

- Database connection loss during write: Transaction rolled back; manufacturer notified; write queued for retry

# 6. Database Architecture Requirements

The system requires a highly normalized relational database (PostgreSQL recommended) with the following core schema. All tables include created_at, updated_at (auto-managed), and created_by foreign key to the users table.

## 6.1 Core Entity Tables

### Table: products

product_id UUID PRIMARY KEY

product_code VARCHAR(50) UNIQUE NOT NULL -- e.g., 'GL-4MM-TG'

product_name VARCHAR(255) NOT NULL -- e.g., '4mm Toughened Glass'

category_id UUID FK -> product_categories

unit_of_measure VARCHAR(50) NOT NULL -- 'sqft', 'units', 'kg', 'rft'

specifications JSONB -- {thickness: '4mm', type: 'toughened'}

is_active BOOLEAN DEFAULT TRUE

created_at TIMESTAMPTZ DEFAULT NOW()

### Table: suppliers

supplier_id UUID PRIMARY KEY

supplier_name VARCHAR(255) NOT NULL

whatsapp_number VARCHAR(20) UNIQUE NOT NULL -- E.164 format: +91XXXXXXXXXX

product_categories UUID[] -- Array of category_ids they supply

is_active BOOLEAN DEFAULT TRUE

rating DECIMAL(3,2) -- Computed from past RFQ performance

onboarded_at TIMESTAMPTZ

### Table: rfq_sessions

rfq_id UUID PRIMARY KEY

rfq_reference VARCHAR(50) UNIQUE -- 'RFQ-2025-0041'

manufacturer_id UUID FK -> users

raw_requirement TEXT -- Original message from manufacturer

parsed_requirements JSONB -- Extracted structured requirement

status ENUM('draft','broadcasted','collecting','comparing','closed','cancelled')

broadcast_at TIMESTAMPTZ

response_deadline TIMESTAMPTZ

created_at TIMESTAMPTZ DEFAULT NOW()

### Table: rfq_line_items

line_item_id UUID PRIMARY KEY

rfq_id UUID FK -> rfq_sessions

product_id UUID FK -> products

quantity_requested DECIMAL(10,3) NOT NULL

unit_of_measure VARCHAR(50)

additional_specs TEXT

### Table: supplier_quotes

quote_id UUID PRIMARY KEY

rfq_id UUID FK -> rfq_sessions

supplier_id UUID FK -> suppliers

submission_method ENUM('text','pdf','image','audio')

raw_content_url TEXT -- WhatsApp media URL or S3 path

parsed_data JSONB -- Full extracted structured quote

extraction_confidence DECIMAL(4,3) -- 0.000 to 1.000

review_required BOOLEAN DEFAULT FALSE

version INTEGER DEFAULT 1 -- For revised quotes

submitted_at TIMESTAMPTZ

is_current_version BOOLEAN DEFAULT TRUE

### Table: quote_line_items

quote_line_id UUID PRIMARY KEY

quote_id UUID FK -> supplier_quotes

rfq_line_item_id UUID FK -> rfq_line_items

product_id UUID FK -> products

unit_price DECIMAL(12,4) NOT NULL

currency VARCHAR(3) DEFAULT 'INR'

gst_rate DECIMAL(5,2)

total_price_excl_gst DECIMAL(14,4)

total_price_incl_gst DECIMAL(14,4)

delivery_days INTEGER

validity_days INTEGER

notes TEXT

source_bounding_box JSONB -- For image/PDF: pixel coordinates

### Table: inventory

inventory_id UUID PRIMARY KEY

product_id UUID FK -> products UNIQUE

current_quantity DECIMAL(12,3) DEFAULT 0

reorder_level DECIMAL(12,3)

warehouse_location VARCHAR(100)

last_updated_by UUID FK -> users

last_updated_at TIMESTAMPTZ

### Table: pricing

pricing_id UUID PRIMARY KEY

product_id UUID FK -> products

supplier_id UUID FK -> suppliers

material_cost DECIMAL(12,4) -- Voice command updates this

selling_price DECIMAL(12,4)

currency VARCHAR(3) DEFAULT 'INR'

effective_from DATE NOT NULL

effective_to DATE

source ENUM('manual','voice_command','rfq_accept','import')

source_reference_id UUID -- rfq_id or voice_note audit_id

is_active BOOLEAN DEFAULT TRUE

### Table: audit_log

audit_id UUID PRIMARY KEY

event_type ENUM('rfq_created','rfq_broadcasted','quote_received','db_updated',...)

entity_type VARCHAR(100) -- 'pricing', 'inventory', etc.

entity_id UUID

old_value JSONB

new_value JSONB

performed_by UUID FK -> users

source_medium ENUM('whatsapp_text','whatsapp_voice','api','admin')

source_artifact_id TEXT -- Voice note ID, message ID, etc.

performed_at TIMESTAMPTZ DEFAULT NOW()

DOCUMENT 2

STATEMENT OF WORK (SOW)

Agentic AI WhatsApp RFQ Bot — MVP Development

# 1. Project Scope

## 1.1 In-Scope for MVP

IN SCOPE — MVP DELIVERABLES

### Core Platform

- FastAPI application with WhatsApp Cloud API webhook integration and HMAC signature validation

- Redis-based conversation state management with session handling per WhatsApp number

- PostgreSQL database with full normalized schema as defined in PRD Section 6

- Asynchronous task processing with Celery + Redis broker

- Docker Compose setup for local development; Docker-ready for cloud deployment

### Workflow 1: RFQ Generation

- LLM-powered natural language requirement parser (intent + entity extraction)

- Structured RFQ generation with unique reference ID and WhatsApp preview

- Supplier broadcast engine (up to 50 suppliers per RFQ)

- Supplier list management (product-category-based filtering)

### Workflow 2: Multimodal Ingestion

- Text quote parser with confidence scoring

- PDF ingestion pipeline: download, image conversion, Vision LLM extraction

- Image/photo OCR pipeline with bounding box traceability

- Audio transcription pipeline (Whisper API) + LLM extraction

- Unified JSON normalization layer across all modalities

- Duplicate submission detection and versioning

### Workflow 3: Comparative Analysis

- Automated quote compilation triggered on deadline or manual command

- WhatsApp-formatted comparative summary table

- Lowest-cost highlighting and missing-supplier flagging

### Workflow 4: Voice-to-DB

- Whisper-based voice command transcription

- Agentic function-calling for intent recognition and entity mapping

- Mandatory confirmation gate before DB writes

- Pricing and inventory table updates

- Full audit logging for all DB mutations

## 1.2 Out-of-Scope (Future Phases)

OUT OF SCOPE — POST-MVP / FUTURE PHASES

- Web-based admin dashboard / UI for non-technical users

- ERP / Tally / SAP integration (batch export files as interim solution)

- Automated supplier onboarding workflow (OTP verification, KYC)

- Multi-tenant architecture (SaaS mode for multiple manufacturers)

- Email and SMS channels (WhatsApp only for MVP)

- Mobile app or web portal for manufacturers

- Predictive pricing analytics and demand forecasting

- Automated purchase order generation and supplier confirmation workflow

- Real-time supplier rating and performance analytics

- Custom LLM fine-tuning on fenestration domain data

# 2. Technical Stack Recommendations

## 2.1 Core Backend

| Component | Recommended Technology | Rationale |
| --- | --- | --- |
| API Framework | FastAPI (Python 3.11+) | Async-native, OpenAPI auto-docs, excellent Pydantic integration |
| Task Queue | Celery + Redis Broker | Handles async LLM calls, retries, and scheduled broadcasts |
| Session Store | Redis 7.x | Sub-millisecond state reads for conversation context; TTL support |
| Database | PostgreSQL 16 + SQLAlchemy 2.0 | JSONB support for flexible specs; ACID compliance for pricing writes |
| ORM / Migrations | SQLAlchemy 2.0 + Alembic | Type-safe models; versioned schema migrations |
| Validation | Pydantic v2 | Runtime type enforcement on all LLM outputs |
| Config Management | python-dotenv + Pydantic Settings | 12-Factor App compliance |

## 2.2 AI / LLM Layer

| Function | Primary Recommendation | Fallback |
| --- | --- | --- |
| Text + Structured Extraction | Claude claude-sonnet-4-20250514 (Anthropic) | GPT-4o (OpenAI) |
| Vision / OCR (PDF + Image) | Claude claude-sonnet-4-20250514 Vision API | GPT-4o Vision |
| Speech-to-Text | OpenAI Whisper API (whisper-1) | Google Speech-to-Text v2 |
| Function Calling / Tool Use | Anthropic Tool Use API | OpenAI Function Calling |
| Orchestration Framework | LangChain (LCEL) or direct API calls | LlamaIndex for RAG (future) |
| Confidence Scoring | Custom logprob-based scoring | LLM self-evaluation prompt |

## 2.3 WhatsApp Integration

| Component | Technology | Notes |
| --- | --- | --- |
| Messaging API | Meta WhatsApp Business Cloud API | Cloud-hosted; no on-premise BSP needed |
| Webhook Handler | FastAPI POST /webhook endpoint | HMAC-256 signature verification on all inbound |
| Media Download | httpx async client + S3/MinIO storage | Download before URL expires (5-min window) |
| Message Templates | WhatsApp Approved Templates | Required for broadcaster-initiated messages |
| Phone Verification | WhatsApp Number as primary identity | Stored in users table; no additional OTP for MVP |

## 2.4 Infrastructure

| Component | Recommendation | Notes |
| --- | --- | --- |
| Containerization | Docker + Docker Compose | All services containerized from day 1 |
| Cloud Platform | AWS (EC2 t3.medium or ECS Fargate) | Cost-effective; S3 for media storage |
| Reverse Proxy | Nginx | SSL termination; rate limiting at edge |
| SSL / TLS | Let's Encrypt (Certbot) | Required for WhatsApp webhook HTTPS |
| Monitoring | Sentry (errors) + Prometheus + Grafana | LLM latency dashboards; error rate alerting |
| Secrets Management | AWS Secrets Manager | Never hardcode API keys |
| CI/CD | GitHub Actions | Lint, test, build, deploy pipeline |

## 2.5 Development Tools & Testing

- Testing: pytest + pytest-asyncio; coverage target >80% for core pipeline

- API Mocking: pytest-httpx for WhatsApp API mocks; factory_boy for DB fixtures

- Code Quality: ruff (linter) + black (formatter) + mypy (type checking)

- API Documentation: Auto-generated FastAPI OpenAPI docs at /docs

- LLM Testing: Prompt regression tests with golden datasets of supplier quotes

# 3. Phased Implementation Plan

## Phase 1: Core Infrastructure & WhatsApp Authentication

Duration: Weeks 1–3 | Est. Effort: 80–100 hours

| Week | Tasks | Deliverables |
| --- | --- | --- |
| Week 1 | Project setup: repo, Docker Compose, GitHub Actions CI pipeline, FastAPI boilerplate, Pydantic settings, Alembic init | Running FastAPI app with health check; Docker Compose with Postgres + Redis |
| Week 2 | WhatsApp Cloud API integration: webhook receiver, HMAC validation, message type routing, inbound message model, outbound message sender service | Functional webhook that echoes messages; outbound text message sending verified |
| Week 3 | Conversation state management (Redis sessions), user/supplier registration flow, product catalog seed data, DB schema migrations for all core tables | Complete DB schema deployed; basic session management; supplier list seeded |

### Phase 1 Acceptance Criteria

- WhatsApp webhook receives and validates messages end-to-end

- Bot can send a text reply to any inbound WhatsApp message

- All database tables created with correct constraints and indexes

- Docker Compose starts all services cleanly; CI pipeline runs green

## Phase 2: RFQ Generation & Multimodal Parsing Pipeline

Duration: Weeks 4–8 | Est. Effort: 160–200 hours

| Week | Tasks | Deliverables |
| --- | --- | --- |
| Week 4 | LLM integration (Anthropic API client, Pydantic output schemas, retry/timeout handling), requirement parser module (entity extraction for product, quantity, unit), RFQ preview generation | Requirement parser: ≥90% accuracy on 50 test inputs |
| Week 5 | RFQ broadcast engine: supplier filtering by category, WhatsApp template-based broadcast, delivery tracking, failed delivery retry queue, RFQ reference ID generation | End-to-end RFQ broadcast to test supplier numbers; retry logic verified |
| Week 6 | Text & Audio quote parsers: unified JSON extractor, Whisper integration, confidence scoring, duplicate detection, quote versioning | Text + audio quote ingestion with structured output; confidence thresholds tested |
| Week 7 | PDF pipeline: async PDF download, pdf2image conversion, Vision LLM extraction, multi-page handling, error handling for corrupt/encrypted PDFs | PDF pipeline tested with 20+ real supplier quote PDFs |
| Week 8 | Image/photo OCR pipeline: image preprocessing, Vision LLM extraction, bounding box logging, low-confidence flagging, integration testing of all modalities end-to-end | All 4 modalities working; unified output schema validated; hallucination guardrails in place |

## Phase 3: Comparison Engine & Agentic Voice-to-DB

Duration: Weeks 9–12 | Est. Effort: 120–150 hours

| Week | Tasks | Deliverables |
| --- | --- | --- |
| Week 9 | Comparative analysis module: quote aggregation, WhatsApp table formatter, lowest cost highlight, missing supplier flagging, auto-trigger on deadline, manual trigger command | Comparison report generated and sent on WhatsApp for test RFQ scenarios |
| Week 10 | Agentic voice-to-DB: intent classification (update_pricing vs update_inventory), entity resolver (product/supplier context lookup), function-calling tool definitions, confirmation message flow | Voice command intent extracted for 90%+ of test cases; confirmation loop working |
| Week 11 | DB write execution: pricing + inventory update services, atomic transactions, rollback handling, audit_log insertion, success/failure notification to manufacturer | Full voice-to-DB flow working end-to-end with audit trail; tested for edge cases |
| Week 12 | Integration testing, performance testing, security review (HMAC, SQL injection, secrets audit), bug fixes, documentation, staging deployment | All acceptance criteria from PRD Section 3 verified; staging environment live |

## 3.1 Timeline Summary

| Phase | Duration & Key Milestone |
| --- | --- |
| Phase 1: Core Infrastructure | Weeks 1–3 ¦ WhatsApp webhook functional + DB schema deployed |
| Phase 2: RFQ + Multimodal Pipeline | Weeks 4–8 ¦ All 4 ingestion modalities working; RFQ broadcast live |
| Phase 3: Comparison + Voice-to-DB | Weeks 9–12 ¦ Full end-to-end flow; voice commands update DB |
| Total MVP Timeline | 12 Weeks (3 Months) |
| Post-MVP Buffer | +2 weeks for UAT, bug fixes, production hardening |

## 3.2 Assumptions & Dependencies

- WhatsApp Business Account and Meta App are created and approved before Phase 1 begins

- Anthropic and OpenAI API keys are available with sufficient quota for development

- A minimum of 5 real supplier phone numbers are available for end-to-end testing by Week 5

- A sample dataset of 20+ supplier quotes in all formats (text, PDF, image, audio) is provided for pipeline testing by Week 6

- Cloud infrastructure (AWS account, domain name, SSL cert) provisioned by Week 3

DOCUMENT 3

WIREFRAMES & USER FLOW

WhatsApp UX Flows + Backend Architecture Sequence

# 1. Manufacturer WhatsApp UX Flow

All messages shown below are the actual WhatsApp conversation experience from the Procurement Manager's perspective. Bot messages are prefixed with [BOT]. Manufacturer actions are prefixed with [USER].

## Flow 1A: Sending a Requirement & RFQ Generation

┌─────────────────────────────────────────────────────────────────────┐

│ WHATSAPP CHAT — Manufacturer's Phone │

├─────────────────────────────────────────────────────────────────────┤

│ │

│ [USER] Need rates for 50 units of 4mm toughened glass 9:01 AM ✓✓│

│ │

│ [BOT] ✅ Requirement Received! 9:01 AM │

│ I've parsed the following: │

│ • Product: 4mm Toughened Glass │

│ • Quantity: 50 Units │

│ • Category: Glass │

│ │

│ What is your required delivery date? │

│ │

│ [USER] By end of this week 9:02 AM ✓✓ │

│ │

│ [BOT] 📋 RFQ Preview — Ref: RFQ-2025-0041 9:02 AM │

│ ───────────────────────────────────── │

│ REQUEST FOR QUOTATION │

│ RFQ Ref: RFQ-2025-0041 │

│ Product: 4mm Toughened Glass │

│ Qty: 50 Units │

│ Required By: 22 Mar 2025 │

│ Response Deadline: 20 Mar 2025, 6 PM │

│ ───────────────────────────────────── │

│ This will be sent to 8 suppliers. │

│ │

│ [ ✅ SEND RFQ ] [ ✏️ EDIT ] [ ❌ CANCEL ] │

│ │

│ [USER] [Taps: ✅ SEND RFQ] 9:03 AM ✓✓ │

│ │

│ [BOT] 🚀 RFQ Broadcasted! 9:03 AM │

│ Sent to 8 suppliers. I'll notify you as │

│ quotes come in. Deadline: 20 Mar, 6 PM. │

│ │

└─────────────────────────────────────────────────────────────────────┘

## Flow 1B: Receiving Quote Notifications

┌─────────────────────────────────────────────────────────────────────┐

│ WHATSAPP CHAT — Manufacturer's Phone (ongoing thread) │

├─────────────────────────────────────────────────────────────────────┤

│ │

│ [BOT] 📥 Quote Received — RFQ-2025-0041 11:30 AM │

│ Supplier: Shah Glass Works │

│ Format: PDF — Parsed ✅ Confidence: 97% │

│ Preview: ₹220/sqft + 18% GST, 5 days delivery │

│ [2 of 8 suppliers responded] │

│ │

│ [BOT] 📥 Quote Received — RFQ-2025-0041 2:15 PM │

│ Supplier: Mehta Glazing Co. │

│ Format: Voice Note — Transcribed ✅ Confidence: 88% │

│ Preview: ₹195/sqft + 18% GST, 7 days delivery │

│ [5 of 8 suppliers responded] │

│ │

│ [BOT] ⚠️ Low Confidence Quote — RFQ-2025-0041 3:45 PM │

│ Supplier: Patel Glass & Aluminium │

│ Format: Image (Handwritten) — Confidence: 71% │

│ Some fields need review. Tap to review: │

│ [ 🔍 REVIEW QUOTE ] │

│ │

└─────────────────────────────────────────────────────────────────────┘

## Flow 1C: Requesting Comparison Report

┌─────────────────────────────────────────────────────────────────────┐

│ WHATSAPP CHAT — Manufacturer's Phone │

├─────────────────────────────────────────────────────────────────────┤

│ │

│ [USER] compare RFQ-2025-0041 6:05 PM ✓✓ │

│ │

│ [BOT] 📊 COMPARISON REPORT — RFQ-2025-0041 6:05 PM │

│ Product: 4mm Toughened Glass ¦ Qty: 50 Units │

│ ════════════════════════════════════════ │

│ SUPPLIER ₹/SQFT GST DAYS TOTAL │

│ ───────────────────────────────────────── │

│ ✅ BEST Mehta Glazing 195 18% 7 11,505 │

│ Shah Glass Works 220 18% 5 12,980 │

│ Rathi Glass Co. 205 18% 6 12,095 │

│ National Glass 215 12% 4 12,040 │

│ ───────────────────────────────────────── │

│ ⏳ Awaiting: JK Glass, Vidhi Glass, Sunrise (3) │

│ ════════════════════════════════════════ │

│ Totals include GST. Based on 50 units @ 10 sqft/unit. │

│ │

└─────────────────────────────────────────────────────────────────────┘

## Flow 1D: Voice-Activated Database Update

┌─────────────────────────────────────────────────────────────────────┐

│ WHATSAPP CHAT — Manufacturer's Phone │

├─────────────────────────────────────────────────────────────────────┤

│ │

│ [USER] [🎤 Voice Note — 8 seconds] 6:10 PM ✓✓ │

│ Transcript: 'p1 material price 195, 30 units' │

│ │

│ [BOT] 🤖 Understood! Please confirm this update: 6:10 PM │

│ ───────────────────────────────────────── │

│ Product: 4mm Toughened Glass [P001] │

│ Supplier: Mehta Glazing Co. │

│ Field: material_cost │

│ New Value: ₹195 per sqft │

│ Inventory: 30 Units → IN STOCK │

│ ───────────────────────────────────────── │

│ [ ✅ YES, UPDATE ] [ ❌ NO, CANCEL ] │

│ │

│ [USER] [Taps: ✅ YES, UPDATE] 6:11 PM ✓✓ │

│ │

│ [BOT] ✅ Database Updated Successfully! 6:11 PM │

│ • pricing.material_cost = ₹195/sqft (Mehta Glazing) │

│ • inventory.current_quantity = 30 Units │

│ Audit Ref: AUD-2025-18842 ¦ Updated: 20 Mar 2025, 6:11 PM │

│ │

└─────────────────────────────────────────────────────────────────────┘

# 2. Supplier WhatsApp UX Flow

This represents the experience on the Supplier's WhatsApp. The supplier does not need to install any app or follow a structured format — they simply reply naturally.

## Flow 2A: Receiving & Responding to an RFQ

┌─────────────────────────────────────────────────────────────────────┐

│ WHATSAPP — Supplier's Phone (Shah Glass Works) │

├─────────────────────────────────────────────────────────────────────┤

│ │

│ [BOT] 📋 REQUEST FOR QUOTATION 9:03 AM │

│ From: Rajesh Fenestration Pvt. Ltd. │

│ RFQ Ref: RFQ-2025-0041 │

│ ───────────────────────────────────────── │

│ Product: 4mm Toughened Glass │

│ Quantity: 50 Units │

│ Delivery Required By: 22 Mar 2025 │

│ Please respond by: 20 Mar 2025, 6 PM │

│ ───────────────────────────────────────── │

│ Please reply with your best rates. │

│ You may reply as: text, PDF, image, or voice note. │

│ │

│ [Supplier options — any of the following is valid:] │

│ │

│ OPTION A — Text reply: │

│ [SUP] RFQ-2025-0041: Rate 220/sqft + 18% GST. 11:20 AM ✓✓ │

│ Delivery 5 days. Valid 15 days. │

│ │

│ OPTION B — PDF attachment: │

│ [SUP] [📎 Quotation_Shah_Glass.pdf] 11:22 AM ✓✓ │

│ │

│ OPTION C — Photo of ledger/printout: │

│ [SUP] [📷 IMG_20250320_112500.jpg] 11:25 AM ✓✓ │

│ │

│ OPTION D — Voice note: │

│ [SUP] [🎤 Voice Note — 12 seconds] 11:28 AM ✓✓ │

│ │

│ [BOT] ✅ Quote Received! (RFQ-2025-0041) 11:30 AM │

│ Thank you, Shah Glass Works. Your quotation │

│ has been recorded: ₹220/sqft + 18% GST, │

│ 5-day delivery, valid 15 days. │

│ The buyer will be in touch with a decision. │

│ │

└─────────────────────────────────────────────────────────────────────┘

## Flow 2B: Error / Retry Scenario

┌─────────────────────────────────────────────────────────────────────┐

│ WHATSAPP — Supplier's Phone (Patel Glass & Aluminium) │

├─────────────────────────────────────────────────────────────────────┤

│ │

│ [SUP] [📷 IMG — blurry handwritten quote] 3:40 PM ✓✓ │

│ │

│ [BOT] ⚠️ Partial Extraction (RFQ-2025-0041) 3:45 PM │

│ We received your image but some details │

│ weren't fully readable: │

│ ✅ Rate: ₹210/sqft ❓ GST Rate: unclear │

│ ❓ Delivery Days: unclear │

│ │

│ Could you reply with just: GST% and delivery days? │

│ e.g. '18% GST, 6 days delivery' │

│ │

│ [SUP] 18 percent GST delivery 6 days 3:48 PM ✓✓ │

│ │

│ [BOT] ✅ Quote Confirmed! (RFQ-2025-0041) 3:48 PM │

│ Patel Glass: ₹210/sqft + 18% GST, 6 days. │

│ Thank you! │

│ │

└─────────────────────────────────────────────────────────────────────┘

# 3. Backend Architecture Flow

This section maps the complete sequence of events from inbound webhook to database update. Each numbered step corresponds to a discrete service or function call in the FastAPI application.

## 3.1 Inbound Message Processing Flow (Webhook → LLM Router)

SEQUENCE: Inbound WhatsApp Message

1. WhatsApp Cloud API ──POST /webhook──► FastAPI Webhook Handler

│ Validate X-Hub-Signature-256 (HMAC-SHA256)

│ If invalid → HTTP 403, log security event, STOP

│ If valid → HTTP 200 (immediate response to Meta)

▼

2. Webhook Handler ──enqueue──► Celery Task Queue (Redis)

│ Purpose: Return 200 to Meta within 200ms (avoid webhook retries)

│ Task payload: {message_id, from_number, message_type, content}

▼

3. Celery Worker picks up task

│ Load conversation state from Redis (key: session:{phone_number})

│ Determine session context: new_user ¦ active_rfq ¦ awaiting_confirmation

▼

4. Message Type Router

│ message_type == 'text' → Text Processing Pipeline

│ message_type == 'audio' → Audio Processing Pipeline

│ message_type == 'document' → PDF Processing Pipeline

│ message_type == 'image' → Image Processing Pipeline

│ message_type == 'interactive' (button reply) → Action Handler

▼

5. Sender Identity Check

│ Look up phone_number in suppliers table

│ Look up phone_number in users (manufacturers) table

│ Unknown number → Quarantine, notify admin

## 3.2 RFQ Generation Flow (Manufacturer → Broadcast)

SEQUENCE: RFQ Generation & Broadcast

5. [Manufacturer text received]

│ Context: user is manufacturer, session_state = 'idle'

▼

6. Requirement Parser (LLM Call #1)

│ Model: Claude Sonnet / GPT-4o

│ System prompt: Fenestration domain expert + structured output schema

│ Extract: {product_name, product_code, quantity, unit, specifications}

│ Pydantic validation on output

│ Missing fields? → Generate clarification question → Send WhatsApp → WAIT

▼

7. RFQ Builder

│ Generate rfq_reference (RFQ-YYYY-NNNN sequential)

│ Create rfq_sessions record (status='draft')

│ Insert rfq_line_items

│ Format RFQ preview message (WhatsApp template)

│ Send preview + quick reply buttons to manufacturer

│ session_state = 'awaiting_rfq_confirmation'

▼

8. Manufacturer confirms (button reply: 'SEND RFQ')

│ Button value = 'confirm_rfq:{rfq_id}'

▼

9. Supplier Broadcast Engine

│ Query suppliers by product_category (match rfq category)

│ Filter: is_active = TRUE

│ For each supplier: spawn async sub-task

│ └── send_whatsapp_template(supplier.whatsapp_number, rfq_data)

│ └── Log delivery attempt in rfq_broadcast_log

│ Update rfq_sessions.status = 'broadcasted'

│ Update rfq_sessions.broadcast_at = NOW()

│ Send confirmation to manufacturer

│ session_state = 'rfq_active:{rfq_id}'

## 3.3 Multimodal Quote Ingestion Flow

SEQUENCE: Supplier Quote Received

10. [Supplier message received — any modality]

│ Identify active RFQ: scan text/caption for RFQ-YYYY-NNNN pattern

│ If no RFQ ref found → check supplier's last active RFQ within 48hrs

│ If still no match → reply asking for RFQ reference

▼

11. Media Acquisition (if non-text)

│ Extract media_id from WhatsApp message payload

│ GET https://graph.facebook.com/v18.0/{media_id} (get download URL)

│ Download file with httpx async client (within 5-min expiry window)

│ Upload to S3/MinIO: s3://rfq-media/{rfq_id}/{supplier_id}/{timestamp}.{ext}

│ Store S3 URL in supplier_quotes.raw_content_url

▼

12. Modality-Specific Parser

│

├── TEXT PATH:

│ └── LLM Call: extract structured quote JSON from text

│

├── AUDIO PATH:

│ ├── Whisper API: audio file → transcript text

│ └── LLM Call: extract structured quote JSON from transcript

│

├── PDF PATH:

│ ├── pdf2image: convert each page to 300dpi PNG

│ ├── Vision LLM Call: extract from each page image

│ └── Merge multi-page results with deduplication

│

└── IMAGE PATH:

├── Preprocess: auto-rotate, enhance contrast (Pillow)

└── Vision LLM Call: extract structured quote JSON

▼

13. Output Normalization & Validation

│ Parse LLM output through QuoteLineItem Pydantic schema

│ Calculate confidence score (logprob average or self-eval)

│ Validate: price range check, cross-field math consistency

│ Flag hallucination risk fields (out-of-range values)

│ Duplicate check: same supplier + same rfq_id already exists?

▼

14. Database Write

│ INSERT supplier_quotes (+ extraction_confidence, review_required flag)

│ INSERT quote_line_items (+ source_bounding_box for image/pdf)

│ UPDATE rfq_sessions (increment response_count)

▼

15. Notifications

│ Send WhatsApp acknowledgement to SUPPLIER (confirmation message)

│ Send WhatsApp notification to MANUFACTURER (quote received alert)

│ If review_required=TRUE: additional flag in manufacturer message

## 3.4 Voice-to-DB Execution Flow

SEQUENCE: Voice Command → DB Update

16. [Manufacturer sends voice note]

│ message_type = 'audio'

│ Sender is manufacturer (not supplier)

│ Load session: context = 'post_comparison' or 'idle'

▼

17. Audio Transcription

│ Download audio file from WhatsApp

│ OpenAI Whisper API: audio → text transcript

│ Language detection: auto (handles en/hi/Hinglish)

▼

18. Intent & Entity Extraction (Agentic Tool Use)

│ LLM Call with Tool Definitions:

│ Tools: [update_pricing, update_inventory, get_comparison, create_rfq]

│ LLM selects tool + extracts parameters from transcript

│ e.g.: update_pricing({product_ref:'p1', field:'material_cost', value:195})

│ + update_inventory({product_ref:'p1', quantity:30, unit:'units'})

▼

19. Entity Resolution

│ product_ref 'p1' → lookup products table + session context

│ If multiple matches → send clarification message → WAIT

│ If confidence < 0.80 → send clarification message → WAIT

│ Resolve supplier context from active RFQ session if applicable

▼

20. Confirmation Gate

│ Format human-readable confirmation message

│ Include: product name, field, old value, new value, quantity

│ Send to manufacturer with YES/NO quick reply buttons

│ session_state = 'awaiting_db_confirm:{operation_hash}'

▼

21. Await Confirmation Reply

│ Button 'YES' received → proceed to step 22

│ Button 'NO' received → cancel, send cancellation msg, reset state

│ Timeout (10 min, no reply) → cancel, notify, reset state

▼

22. Atomic Database Write

│ BEGIN TRANSACTION

│ ├── UPDATE pricing SET material_cost=195 WHERE product_id=...

│ │ AND (set effective_from=TODAY, is_active=TRUE, source='voice_cmd')

│ ├── UPDATE inventory SET current_quantity=30 WHERE product_id=...

│ ├── INSERT audit_log (event_type, entity, old_val, new_val, source)

│ └── COMMIT

│ On error: ROLLBACK → notify manufacturer → log error

▼

23. Success Notification

│ Send formatted success message to manufacturer

│ Include: audit reference ID, timestamp, changed values

│ Reset session_state = 'idle'

## 3.5 Service Architecture Diagram (Text Representation)

┌─────────────────────────────────────────────────────────────────────┐

│ SYSTEM ARCHITECTURE — MVP │

├─────────────────────────────────────────────────────────────────────┤

│ │

│ WhatsApp Users External APIs │

│ (Mfr + Suppliers) (Meta / OpenAI / Anthropic) │

│ │ │ │

│ ▼ ▼ │

│ ┌─────────────┐ HTTPS ┌────────────────────────┐ │

│ │ Meta Cloud │ ────────► │ Nginx Reverse Proxy │ │

│ │ API + CDN │ ◄──────── │ (SSL Termination, │ │

│ └─────────────┘ │ Rate Limiting) │ │

│ └──────────┬─────────────┘ │

│ │ │

│ ┌──────────▼─────────────┐ │

│ │ FastAPI Application │ │

│ │ /webhook /health │ │

│ │ (Async, HMAC auth) │ │

│ └──────────┬─────────────┘ │

│ │ enqueue │

│ ┌──────────────────▼──────────────────┐ │

│ │ Redis (Broker + Cache) │ │

│ │ • Celery Task Queue │ │

│ │ • Conversation Sessions (TTL:24h) │ │

│ └──────────────────┬──────────────────┘ │

│ │ consume │

│ ┌────────────────────────▼──────────────────────┐ │

│ │ Celery Workers (Auto-scaled) │ │

│ │ │ │

│ ┌───────────▼────────┐ ┌────────────────┐ ┌────────────┐ │ │

│ │ Text/Intent LLM │ │ Vision LLM │ │ Whisper │ │ │

│ │ (Claude/GPT-4o) │ │ (Claude Vision)│ │ STT API │ │ │

│ └────────────────────┘ └────────────────┘ └────────────┘ │ │

│ │ │ │

│ ┌───────────▼────────────────────────────────────────────┐ │ │

│ │ Normalization + Validation Layer │ │ │

│ │ (Pydantic schemas, confidence scoring, range checks) │ │ │

│ └───────────┬────────────────────────────────────────────┘ │ │

│ └───────────────────────────────┘ │ │

│ │ read/write │ │

│ ┌───────────▼───────────────┐ │ │

│ │ PostgreSQL 16 │ │ │

│ │ • products, suppliers │ │ │

│ │ • rfq_sessions, quotes │ │ │

│ │ • inventory, pricing │ │ │

│ │ • audit_log │ │ │

│ └───────────────────────────┘ │ │

│ │ │

│ ┌───────────────────────────┐ │ │

│ │ AWS S3 / MinIO │ │ │

│ │ • PDF, image, audio files │ │ │

│ │ • rfq-media/{rfq}/{sup}/ │ │ │

│ └───────────────────────────┘ │ │

└─────────────────────────────────────────────────────────────────┘