# WhatsApp SaaS Platform - Complete Project Task Breakdown

## Project Overview

Building a multi-tenant WhatsApp Business SaaS platform supporting: - New number provisioning (Scenario A) - Existing number integration via Coexistence/Migration (Scenario B) - RFQ Bot functionality for fenestration industry - Multi-tenant architecture with secure credential management

## Assumptions

- Developer Profile: Junior AI/ML Engineer (2 years experience, Python backend knowledge)

- Work Schedule: 8 hours/day, 5 days/week

- Tech Stack: Python (FastAPI/Flask), PostgreSQL, Redis, Docker

- Meta Partner Status: Assumed to be obtained (external dependency)

# PART 1: POC (Proof of Concept) - Scenario A Only

## Objective

Build a working prototype supporting new number provisioning with basic messaging capabilities.

## WITH AI TOOLS (Cursor, GitHub Copilot, ChatGPT, Claude)

### Week 1: Foundation & Setup (5 days)

#### Day 1: Environment & Architecture Design

Hours 1-2: Project initialization - Set up Git repository - Create project structure using AI templates - Initialize virtual environment and dependencies

Hours 3-4: Database schema design - Use AI to generate PostgreSQL schema for: - Tenants table - WABA credentials table - Messages table - Webhooks log table - Review and adjust AI-generated schema

Hours 5-6: Meta Business API research - Study Meta Embedded Signup documentation - Test Meta Graph API explorer - Understand webhook structure

Hours 7-8: Development environment setup - Install Docker, PostgreSQL, Redis - Configure local development environment - Set up ngrok for webhook testing

#### Day 2: Core Backend Framework

Hours 1-3: FastAPI application setup - Use AI to scaffold FastAPI application - Implement basic routing structure - Set up SQLAlchemy ORM models (AI-assisted)

Hours 4-6: Database layer implementation - Create database connection manager - Implement CRUD operations for tenants - Add migration scripts using Alembic (AI-generated)

Hours 7-8: Configuration management - Environment variables setup - Secrets management design - Create configuration classes

#### Day 3: Meta Embedded Signup Integration

Hours 1-3: Embedded Signup flow - Frontend - Create simple signup page using AI-generated HTML/JS - Implement Meta OAuth callback handling - Add loading states and error handling

Hours 4-6: Embedded Signup flow - Backend - Exchange authorization code for tokens (AI-assisted) - Store WABA credentials securely - Implement tenant creation logic

Hours 7-8: Testing & debugging - Test complete signup flow - Handle edge cases - Debug token refresh logic

#### Day 4: Webhook Infrastructure

Hours 1-3: Webhook endpoint setup - Create webhook verification endpoint - Implement signature validation (AI-generated) - Set up webhook subscription

Hours 4-6: Message receiving logic - Parse incoming webhook payloads - Store messages in database - Implement tenant resolution logic

Hours 7-8: Webhook testing - Use Meta’s webhook testing tools - Test with real messages - Add comprehensive logging

#### Day 5: Message Sending Functionality

Hours 1-3: Cloud API integration - Implement send message function (AI-assisted) - Handle different message types (text, media) - Error handling and retry logic

Hours 4-5: Basic rate limiting - Implement request throttling - Add queue system using Redis

Hours 6-8: POC testing & documentation - End-to-end testing - Create basic API documentation (AI-generated) - Record demo video

### POC Delivery: 5 days

POC Capabilities: ✅ New tenant onboarding via Embedded Signup ✅ Receive messages via webhooks ✅ Send text messages to customers ✅ Multi-tenant credential isolation ✅ Basic logging and error handling

## WITHOUT AI TOOLS (Traditional Development)

### Week 1-2: Foundation & Setup (7 days)

#### Day 1-2: Environment & Architecture Design

Day 1: - Manual project structure creation - Research FastAPI best practices - Design database schema from scratch - Set up development environment

Day 2: - Manually write SQLAlchemy models - Create database migration scripts - Test database connections - Configuration management setup

#### Day 3-4: Meta Business API Integration

Day 3: - Deep dive into Meta documentation - Manual implementation of OAuth flow - Create signup page HTML/CSS/JS manually - Debug authentication issues

Day 4: - Complete Embedded Signup backend - Implement token storage and refresh - Manual testing and debugging - Handle error cases

#### Day 5-6: Webhook Implementation

Day 5: - Manual webhook endpoint creation - Research webhook signature validation - Implement verification logic - Set up webhook subscriptions

Day 6: - Parse webhook payloads manually - Implement message storage logic - Create tenant resolution system - Extensive testing and debugging

#### Day 7: Message Sending & POC Testing

Hours 1-4: Cloud API message sending - Research Cloud API documentation - Manually implement send message function - Handle errors and retries

Hours 5-8: POC testing - End-to-end testing - Bug fixes - Basic documentation

### POC Delivery: 7 days

# PART 2: FULL PRODUCTION SYSTEM

## Objective

Build a complete, production-ready WhatsApp SaaS platform with both scenarios, RFQ bot, and enterprise features.

## WITH AI TOOLS

### Week 2-3: Advanced Features (10 days)

#### Day 6-7: Scenario B - Coexistence Mode

Day 6: - Research coexistence API endpoints - Implement QR code authentication flow (AI-assisted) - Add chat history import functionality

Day 7: - Test coexistence mode - Handle synchronization logic - Document coexistence setup

#### Day 8-9: Scenario B - Number Migration

Day 8: - Implement migration initiation flow - Handle source WABA disconnection - Template migration logic (AI-generated)

Day 9: - Test migration scenarios - Handle edge cases and errors - Create migration guide

#### Day 10: Template Management System

- CRUD operations for message templates (AI-assisted)

- Template approval workflow

- Template versioning

#### Day 11-12: Multi-tenant Security Enhancements

Day 11: - Implement tenant isolation middleware - Add API key authentication (AI-generated) - Role-based access control (RBAC)

Day 12: - Encrypt sensitive credentials (Fernet/KMS) - Implement audit logging - Security testing

#### Day 13-14: RFQ Bot - Core Logic

Day 13: - Design conversation flow state machine - Implement intent recognition (basic NLP, AI-assisted) - Create response templates for fenestration RFQ

Day 14: - Implement context management - Add conversation state persistence - Test bot conversation flows

#### Day 15: RFQ Bot - Data Extraction

- Extract product specifications from messages (AI-assisted)

- Parse dimensions, materials, quantities

- Validate and structure RFQ data

- Store RFQ submissions

### Week 4: Advanced RFQ Bot & Integrations (5 days)

#### Day 16-17: AI/ML Integration for RFQ

Day 16: - Integrate OpenAI/Anthropic API for intelligent responses - Implement RAG (Retrieval Augmented Generation) for product knowledge - Create vector database for product specifications (AI-assisted)

Day 17: - Fine-tune responses for fenestration domain - Add image recognition for product photos - Test AI response quality

#### Day 18: Quote Generation System

- Create quote calculation logic (AI-assisted)

- PDF quote generation (using reportlab)

- Email/WhatsApp quote delivery

- Quote tracking and follow-up

#### Day 19: CRM Integration Preparation

- Design webhook system for external integrations

- Create REST API for CRM data sync (AI-generated)

- Implement quote export functionality

#### Day 20: Admin Dashboard - Backend

- Create admin API endpoints (AI-assisted)

- Analytics and reporting endpoints

- Tenant management APIs

- Message logs and search functionality

### Week 5: Frontend & DevOps (5 days)

#### Day 21-22: Admin Dashboard - Frontend

Day 21: - React/Vue.js dashboard setup (AI-scaffolded) - Tenant management UI - Real-time message viewer

Day 22: - Analytics dashboard with charts - Template management UI - Settings and configuration pages

#### Day 23: Testing & Quality Assurance

- Write unit tests (AI-generated test cases)

- Integration tests for all workflows

- Load testing with simulated traffic

- Security testing (OWASP top 10)

#### Day 24: DevOps & Deployment

- Dockerize application (AI-generated Dockerfiles)

- Set up CI/CD pipeline (GitHub Actions, AI-assisted)

- Configure production environment (AWS/GCP)

- Database migration scripts for production

#### Day 25: Documentation & Handoff

- API documentation with Swagger/OpenAPI (AI-generated)

- User guides and setup instructions

- Architecture diagrams (AI-assisted)

- Video tutorials

### Full System Delivery: 25 days (5 weeks)

## WITHOUT AI TOOLS

### Week 2-4: Advanced Features (15 days)

#### Day 8-10: Scenario B Implementation (3 days)

- Manual research and implementation of coexistence

- Number migration logic from scratch

- Extensive testing and debugging

#### Day 11-13: Security & Multi-tenancy (3 days)

- Manual implementation of RBAC

- Encryption logic from scratch

- Security audit and testing

#### Day 14-17: RFQ Bot Core (4 days)

- Manual state machine design

- Rule-based NLP from scratch

- Conversation flow implementation

- Data extraction logic

#### Day 18-20: Advanced RFQ Features (3 days)

- Manual integration with AI APIs

- Quote generation system

- Testing and refinement

#### Day 21-22: CRM Integration (2 days)

- API design and implementation

- Integration testing

### Week 5-6: Frontend & Deployment (10 days)

#### Day 23-27: Admin Dashboard (5 days)

- Manual React/Vue.js development

- All UI components from scratch

- Styling and responsive design

- Frontend-backend integration

#### Day 28-30: Testing (3 days)

- Manual test case creation

- Comprehensive testing

- Bug fixes and optimization

#### Day 31-32: DevOps & Documentation (2 days)

- Manual Docker configuration

- Deployment setup

- Documentation writing

### Full System Delivery: 32 days (6.4 weeks)

# DETAILED COMPARISON SUMMARY

## POC (Scenario A Only)

| Aspect | With AI Tools | Without AI Tools |
| --- | --- | --- |
| Duration | 5 days | 7 days |
| Code Quality | High (AI best practices) | Medium (learning curve) |
| Testing Coverage | Good (AI-generated tests) | Basic |
| Documentation | Comprehensive (AI-assisted) | Minimal |
| Debugging Time | Lower (AI helps identify issues) | Higher |

## Full Production System

| Aspect | With AI Tools | Without AI Tools |
| --- | --- | --- |
| Duration | 25 days (5 weeks) | 32 days (6.4 weeks) |
| Features Included | All scenarios + RFQ bot + Dashboard | All scenarios + RFQ bot + Dashboard |
| Code Quality | High | Medium-High |
| Maintainability | Excellent | Good |
| Test Coverage | 70-80% | 40-50% |
| Documentation | Comprehensive | Adequate |
| Time Saved | ~30% | Baseline |

# CRITICAL PATH DEPENDENCIES

## External Dependencies (Not in developer control)

- Meta Business Partner Approval: 2-4 weeks (prerequisite)

- WhatsApp Business Account Setup: 1-3 days

- Phone Number Verification: 1-2 days

- Production Environment Provisioning: 2-5 days

## Technical Risks & Mitigation

### High Risk

- Meta API changes: Follow official SDK, use webhooks versioning

- Rate limiting issues: Implement proper queue system early

- Webhook reliability: Add retry logic and idempotency

### Medium Risk

- AI API costs: Set usage limits, implement caching

- Database scalability: Design with sharding in mind

- Multi-tenant data isolation: Thorough testing required

# RECOMMENDED APPROACH

## For POC (Get Started Quickly)

Recommendation: Use AI tools heavily - Timeline: 5 days - Focus: Scenario A only, basic messaging - Goal: Demonstrate feasibility, get stakeholder buy-in

## For Production System

Recommendation: Hybrid approach - Timeline: 25-28 days with AI tools - Strategy: - Use AI for boilerplate and standard patterns - Manual implementation for critical business logic - AI-assisted testing and documentation - Human review of all AI-generated security code

# RESOURCE REQUIREMENTS

## Development Tools

- Free: VS Code, Git, Docker, PostgreSQL, Redis

- Paid (Optional): Cursor ($20/mo), GitHub Copilot ($10/mo)

- Cloud: AWS/GCP free tier initially, ~$50-100/mo for production

## Third-Party Services

- Meta WhatsApp Business API: Free (pay per conversation)

- OpenAI API: ~$20-50 for POC testing

- Hosting: ~$50-200/mo depending on scale

# SUCCESS METRICS

## POC Success Criteria

✅ Successfully onboard 1 test tenant ✅ Send and receive 100+ messages ✅ Zero data leakage between tenants ✅ <2 second webhook response time ✅ Basic error handling works

## Production Success Criteria

✅ Support both Scenario A and B ✅ Handle 1000+ messages/day per tenant ✅ 99.5% webhook processing success rate ✅ RFQ bot extracts data with >90% accuracy ✅ Complete admin dashboard functional ✅ Full API documentation ✅ Automated deployment pipeline

# FINAL RECOMMENDATION

For a junior engineer with 2 years of experience:

### With AI Tools:

- POC: 5 days (1 week)

- Production: 25 days (5 weeks)

- Total: 30 days (6 weeks)

### Without AI Tools:

- POC: 7 days (1.4 weeks)

- Production: 32 days (6.4 weeks)

- Total: 39 days (7.8 weeks)

Time Saved with AI: ~9 days (23%)

### Critical Success Factors:

- Start with POC to validate approach

- Get Meta Partner approval ASAP (parallel track)

- Use AI tools for productivity boost

- Focus on core features first, iterate based on feedback

- Maintain daily progress documentation

- Schedule weekly stakeholder demos

### Phase-wise Budget:

- Phase 1 (POC): Week 1

- Phase 2 (Full Scenario A + B): Weeks 2-3

- Phase 3 (RFQ Bot): Week 4

- Phase 4 (Dashboard + Deployment): Week 5

- Phase 5 (Testing + Polish): Buffer days

Confidence Level: High for POC (80%), Medium-High for full system (70%) given junior developer experience level.